PRIORITISED PRODUCT BACKLOG

Adaptive Learning Platform

All 113 user stories story-pointed, prioritised, sprint-scheduled, and dependency-mapped across 10 epics and 4 delivery sprints. Includes MVP definition, velocity model, and sprint capacity plan.

| Attribute | Value |
| --- | --- |
| Document title | Prioritised Product Backlog — Adaptive Learning Platform |
| Version | 1.0 — Sprint 0 Baseline |
| Status | Active — reviewed at every sprint planning ceremony |
| Date | April 2026 |
| Total stories | 113 user stories across 10 epics + 12 technical stories (Sprint 0) |
| Total story points | 782 SP across all 113 stories (Sprint 0 technical: 89 SP separate) |
| Sprint velocity target | 170–190 SP per sprint (4 sprints × 2 weeks) |
| MVP definition | All P0 stories across Sprints 1–2 (authentication, quiz, basic analytics, payments) |
| Prioritisation method | MoSCoW + Business Value + Risk + Dependency ordering |
| Based on | User Stories v2.0 · BRD v2.0 · PRD v1.0 · RTM v1.0 |
| Review cadence | Backlog groomed every sprint. Re-prioritised at phase gate. |
| Classification | CONFIDENTIAL — Internal Product & Engineering Use Only |

# Table of Contents

1.  Prioritisation Framework & Scoring Model

2.  Epic Summary & Story Point Distribution

3.  MVP Definition & Launch Criteria

4.  Sprint Capacity Model & Velocity Plan

5.  Sprint 0 — Foundation & Setup (Weeks 1–2)

6.  Sprint 1 — Core Platform: Auth, Onboarding, Quiz Engine (Weeks 3–4)

7.  Sprint 2 — Learning Engine, Analytics, Payments (Weeks 5–6)

8.  Sprint 3 — Community, Creator, Moderation (Weeks 7–8)

9.  Sprint 4 — Admin, Institution, Polish, Launch Prep (Weeks 9–10)

10.  Full Prioritised Backlog (All 113 Stories — Landscape)

11.  Dependency Map

12.  Backlog Health Metrics & Definition of Ready

# 1. Prioritisation Framework & Scoring Model

Every story in this backlog is prioritised using a composite score that combines four factors: Business Value, Risk/Dependency weight, MoSCoW classification, and Strategic Objective alignment. The final sprint assignment is the output of this scoring, reviewed and ratified by the Product Owner.

## 1.1 Priority Tiers

| Tier | Label | Definition | Backlog treatment |
| --- | --- | --- | --- |
| P0 | Must-have for launch | Platform cannot launch without this. Core user journey or compliance requirement. Zero exceptions. | Sprint 1 or Sprint 2 only. Never deferred. |
| P1 | Should have | Significant value. Launch is possible without it but user experience is materially worse. | Sprint 2 or Sprint 3. Can be deferred one sprint if capacity forces it. |
| P2 | Could have | Nice to have. Adds polish or covers edge cases. No meaningful impact on core value proposition. | Sprint 3 or Sprint 4. First to be cut if velocity falls behind. |
| Won't | Not this release | Acknowledged. Valuable for Phase 2. Not in scope for Phase 1 launch. | Parking lot. Not in sprint planning. Reviewed at Phase 2 kick-off. |

## 1.2 Story Point Scale (Fibonacci)

| Points | Complexity | Typical effort | Examples |
| --- | --- | --- | --- |
| 1 | Trivial | < 2 hours | Static text page, simple config value, read-only API endpoint with no business logic |
| 2 | Simple | Half a day | CRUD endpoint with validation, simple UI component, unit test suite for existing logic |
| 3 | Small | 1 day | Feature with 2–3 API calls, form with validation + backend, basic analytics query |
| 5 | Medium | 2–3 days | Feature spanning frontend + backend + tests, quiz session logic, auth flow |
| 8 | Large | 3–5 days | Complex feature: adaptive engine integration, payment flow, real-time WebSocket feature |
| 13 | X-Large | 1 week | Entire subsystem: bulk upload pipeline, full moderation workflow, institution analytics |
| 21 | Epic-size | ≥ 1.5 weeks | Split before Sprint Planning. A 21 is a sign the story needs decomposition. |

## 1.3 MoSCoW vs Priority Tier Relationship

| MoSCoW | Maps to priority tier | Sprint assignment rule |
| --- | --- | --- |
| Must have | P0 — Must have for launch | Always Sprint 1 or Sprint 2. Product Owner cannot defer P0/Must stories past Sprint 2. |
| Should have | P1 — Should have | Sprint 2, 3, or 4. Can be deferred one sprint under capacity pressure with PO sign-off. |
| Could have | P2 — Could have | Sprint 3 or Sprint 4. Cut first if velocity falls below 160 SP in any sprint. |
| Won't have | Won't — Not this release | Not scheduled. Added to Phase 2 parking lot with brief description and estimated size. |

# 2. Epic Summary & Story Point Distribution

10 product epics span the full platform. Story points are estimated using planning poker with the full engineering team. The distribution shows that Quiz & Practice (the core product loop) and Admin & Platform Operations carry the highest technical complexity.

| Epic | Epic ID | Stories | Total SP | P0 SP | P1 SP | P2 SP | Primary sprints |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Guest Experience & Acquisition | EPIC-01 | 8 | 42 | 35 | 7 | 0 | Sprint 1 |
| Authentication & Identity | EPIC-02 | 11 | 58 | 55 | 3 | 0 | Sprint 1 |
| Student Profile & Onboarding | EPIC-03 | 9 | 38 | 18 | 20 | 0 | Sprint 1–2 |
| Content Discovery | EPIC-04 | 10 | 44 | 22 | 18 | 4 | Sprint 2 |
| Quiz & Practice Engine | EPIC-05 | 14 | 89 | 65 | 19 | 5 | Sprint 1–2 |
| Analytics & Progress | EPIC-06 | 11 | 63 | 30 | 26 | 7 | Sprint 2–3 |
| Post-Exam Experience | EPIC-07 | 8 | 31 | 8 | 18 | 5 | Sprint 3–4 |
| Expert & Teacher Workflows | EPIC-08 | 18 | 98 | 52 | 40 | 6 | Sprint 2–3 |
| Moderation System | EPIC-09 | 12 | 72 | 72 | 0 | 0 | Sprint 3 |
| Platform Administration | EPIC-10 | 20 | 147 | 82 | 55 | 10 | Sprint 3–4 |
| TOTAL |  | 113 | 782 SP | 439 SP (56%) | 206 SP (26%) | 37 SP (5%) |  |

## 2.1 Sprint Point Load Distribution

| Sprint | Weeks | Total SP | P0 SP | P1 SP | P2 SP | Epics covered | Confidence |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint 0 | 1–2 | 89 (tech) | 89 | 0 | 0 | Infrastructure, CI/CD, repo setup, DB schema | High |
| Sprint 1 | 3–4 | 183 SP | 168 | 15 | 0 | EPIC-01 (full), EPIC-02 (full), EPIC-03 (partial), EPIC-05 (partial) | High |
| Sprint 2 | 5–6 | 187 SP | 175 | 12 | 0 | EPIC-03 (remainder), EPIC-04 (P0), EPIC-05 (remainder), EPIC-06 (P0) | High |
| Sprint 3 | 7–8 | 212 SP | 96 | 106 | 10 | EPIC-07 (partial), EPIC-08 (full), EPIC-09 (full), EPIC-10 (partial) | Medium |
| Sprint 4 | 9–10 | 200 SP | 0 | 93 | 27 | EPIC-06 (P1 remainder), EPIC-07 (remainder), EPIC-10 (remainder), Polish | Medium |
| Total |  | 871 SP (incl Sprint 0) | 528 | 226 | 37 | All 10 epics | — |

Note: Sprint 3 is deliberately heavier at 212 SP because EPIC-09 (Moderation) has zero P0 stories that cannot be done in Sprint 3 — they must be done together as a complete workflow. If velocity is tracking low at end of Sprint 2, EPIC-10 P2 stories are cut first.

# 3. MVP Definition & Launch Criteria

The Minimum Viable Product is defined as the smallest set of stories that delivers a complete, working, monetisable platform. A student can register, take adaptive quizzes, see their readiness score, upgrade to premium, and study from approved content. A creator can upload questions that pass moderation and appear in the quiz bank. An admin can manage the platform.

## 3.1 MVP Story Set (P0 stories — Sprints 1 & 2 only)

| MVP component | Stories included | SP | Without this... |
| --- | --- | --- | --- |
| Guest screening test | STU-REQ-00A through 00H (8 stories) | 42 | No top-of-funnel. Cannot acquire users without paid marketing. |
| Registration & login | STU-REQ-01 through 11 (11 stories) | 58 | No users. Platform is inaccessible. |
| Exam selection gate | STU-REQ-12, 13, 18 (3 stories) | 14 | Students get stuck in onboarding. Cannot proceed. |
| Content catalogue (browse) | STU-REQ-24, 25, 26, 27 (4 stories) | 18 | Students cannot find content. Explore tab is empty. |
| Practice quiz (PRACTICE mode) | STU-REQ-31, 34, 35, 36, 37 (5 stories) | 30 | Core product loop broken. No quizzes = no value. |
| Adaptive quiz (ADAPTIVE mode) | STU-REQ-32 + engine integration (2 stories) | 13 | Premium differentiator missing. Cannot charge for adaptive. |
| Quiz results + breakdown | STU-REQ-37, 39 (2 stories) | 10 | No feedback after quiz. Product loop incomplete. |
| Basic analytics dashboard | STU-REQ-45, 48, 50 (3 stories) | 16 | Students cannot see progress. No reason to return. |
| Readiness score (premium) | STU-REQ-45, 46 + score engine (3 stories) | 18 | No premium differentiation. Cannot monetise. |
| Subscription + payment | Payment Service stories (4 stories) | 24 | Cannot charge for premium. Zero revenue. |
| Question upload + moderation | EXP-REQ-10, 11, 12, MOD-REQ-03–06 (8 stories) | 45 | No content in quiz bank. Cannot run quizzes. |
| Exam syllabus configuration | ADM-REQ-15, 16 (2 stories) | 10 | Platform has no exam structure. Nothing works. |
| Platform admin basics | ADM-REQ-01, 03, 04, 19 (4 stories) | 25 | No moderation, no user management, no audit log. |
| TOTAL MVP | 57 stories | 323 SP | Launch is not possible |

## 3.2 Launch Go/No-Go Criteria

| Criterion | Measurement | Gate level |
| --- | --- | --- |
| All P0 stories accepted by QA | Zero P0 stories with open bugs at Priority 1. Maximum 3 open bugs at Priority 2. | Hard gate — cannot launch |
| Readiness score accuracy ≥ 70% | Test with 50 synthetic student journeys. Score delta vs ground truth < 15 points on average. | Hard gate — cannot launch |
| Payment flow working end-to-end | Stripe test mode: 100% of test payment scenarios pass. Live mode verified with 3 real transactions. | Hard gate — cannot launch |
| Quiz result latency < 500ms p95 | k6 load test: 500 concurrent users, quiz submit endpoint, p95 < 500ms sustained for 10 min. | Hard gate — cannot launch |
| API availability > 99.9% in staging for 7 days | Grafana SLO dashboard: 7-day rolling window on staging environment. | Hard gate — cannot launch |
| Security pen test: zero CRITICAL findings | Third-party pen test report delivered. All CRITICAL findings remediated. | Hard gate — cannot launch |
| DPDP/GDPR: ToS, Privacy Policy, data export API | Legal sign-off. Data export API tested with synthetic accounts. | Hard gate — cannot launch |
| Minimum question bank: 200 per major exam | NEET: ≥200. JEE: ≥200. Questions approved by moderators. | Soft gate — can launch with 150 if expert upload ongoing |
| Creator onboarding: ≥3 approved expert creators | At least 3 experts have completed KYC and uploaded approved questions. | Soft gate — can launch with 2 |
| App Store / Play Store review passed | iOS build approved by Apple. Android bundle approved by Google Play. | Hard gate — mobile cannot launch |

# 4. Sprint Capacity Model & Velocity Plan

The delivery team operates in 5 two-week sprints (Sprint 0 through Sprint 4 — 10 weeks total). Velocity is calculated based on team composition. Story points target is set conservatively in early sprints and increases as the team stabilises.

## 4.1 Team Composition & Capacity

| Role | Count | SP contribution/sprint | Notes |
| --- | --- | --- | --- |
| Engineering Lead (Tech Lead) | 1 | 20 SP | Architecture decisions, code review, unblocking. Not full-time coding. |
| Backend Engineers (Go + Python) | 3 | 40 SP each = 120 SP | Primary API and service implementation. 80% coding capacity. |
| Frontend Engineer (Next.js/React) | 2 | 30 SP each = 60 SP | Web app + admin portal. 80% coding capacity. |
| Mobile Engineers (iOS + Android) | 2 | 25 SP each = 50 SP | Native apps. Platform-specific work takes longer. |
| DevOps / Infrastructure | 1 | 20 SP | Infrastructure, CI/CD, env support. Split across tasks. |
| Data / ML Engineer | 1 | 20 SP | Adaptive engine, analytics. Deep technical work — conservative estimate. |
| QA Lead | 1 | 20 SP (test authoring + execution) | Test cases, regression, sign-off. No feature coding. |
| UI/UX Designer | 1 | 0 SP (design, not code) | Designs 1 sprint ahead. Does not contribute to story points. |
| TOTAL team | 12 | ~190 SP raw capacity | After 15% buffer (ceremonies, bugs, review): ~160–180 SP effective |

## 4.2 Sprint Velocity Plan

| Sprint | Duration | Raw SP capacity | Buffer & overhead | Target SP | Rationale |
| --- | --- | --- | --- | --- | --- |
| Sprint 0 | Weeks 1–2 | 190 SP capacity | 50% overhead — setup, onboarding, tooling | 89 SP (tech only) | Sprint 0 is all technical setup. No feature stories. Overhead is high as team onboards. |
| Sprint 1 | Weeks 3–4 | 190 SP capacity | 15% buffer for unknowns | 160–175 SP | Team warmed up. Core flows well-understood. Conservative velocity. |
| Sprint 2 | Weeks 5–6 | 190 SP capacity | 12% buffer | 165–185 SP | Team in full flow. Velocity peaks. Payment integration adds risk — buffer maintained. |
| Sprint 3 | Weeks 7–8 | 190 SP capacity | 15% buffer (Moderation is complex) | 160–175 SP | Moderation and admin are complex, security-sensitive. Buffer retained. |
| Sprint 4 | Weeks 9–10 | 190 SP capacity | 20% buffer (stabilisation, bug fixing) | 150–165 SP | Final sprint: 30% time for regression, load testing, pen test support, launch prep. |

## 4.3 Risk Buffer — Story Cutting Priority

If velocity falls below target in any sprint, stories are cut in the following priority order. P0 stories are never cut.

| Cut order | Stories | Rationale |
| --- | --- | --- |
| Cut first | All P2 stories in the at-risk sprint | Lowest value. Can ship without these. |
| Cut second | P1 stories in EPIC-07 (Post-exam experience) | Nice-to-have — no active users yet on Phase 1 launch. |
| Cut third | P1 stories in EPIC-06 (Score history chart, Share link) | Analytics extras. Core readiness score is P0 and stays. |
| Cut fourth | P1 stories in EPIC-10 (Admin extras: impersonation, announcement) | Admin can operate without these for first few weeks post-launch. |
| Never cut | All P0 stories. All moderation stories (EPIC-09 — must be complete workflow). | Non-negotiable. Cutting P0 = delaying launch. |

# 5. Sprint 0 — Foundation & Setup (Weeks 1–2)

Sprint 0 contains no feature stories. All work is technical foundation that must be complete before Sprint 1 feature work begins. The Definition of Done for Sprint 0 is: every engineer can run the full local development stack, CI/CD deploys to dev, and all data stores are accessible from pods.

| Technical story | SP | Owner | Done when |
| --- | --- | --- | --- |
| Repository structure: monorepo or polyrepo decision. Branch strategy. PR template. Commit conventions documented. | 3 | Engineering Lead | Team agrees and documents in team_agreements.md |
| AWS account structure: 4 accounts created (dev, staging, prod, security). AWS Organisation configured. SCPs applied. | 5 | DevOps | terragrunt plan shows 0 changes on all accounts. |
| Terraform + Terragrunt: modules for VPC, EKS, Aurora, Redis, S3, Secrets Manager, IAM written and applied to dev. | 13 | DevOps | kubectl get nodes shows nodes in dev cluster. |
| EKS cluster (dev): cluster created, node groups running, namespaces created, network policies applied. | 8 | DevOps | kubectl get pods -A — all kube-system pods Running. |
| Aurora PostgreSQL (dev): cluster created. Flyway baseline migration (V001) run. All 9 schemas created. | 5 | Backend | psql connection from pod succeeds. All schemas present. |
| Redis ElastiCache (dev): cluster created. AUTH configured. TLS enabled. | 3 | DevOps | Redis PING from pod returns PONG. |
| Secrets Manager: all secret placeholders created. ASCP CSI driver installed. Test secret mounted in test pod. | 5 | DevOps | Test pod reads /mnt/secrets/test and prints value. |
| CI/CD: GitHub Actions workflows (pr-check, build-deploy-dev, release). ArgoCD installed. App-of-apps synced. | 8 | DevOps | Push commit → image built → deployed to dev automatically. |
| Docker: base Dockerfile standards documented. Multi-stage distroless templates for Go and Python created. | 3 | Engineering Lead | docker build succeeds for both templates. Trivy scan: 0 CRITICAL. |
| OpenSearch (dev): domain created. EN analyser confirmed. Test document indexed and searched. | 3 | DevOps | OpenSearch API returns result for test query. |
| Monitoring: Prometheus + Grafana + Loki + Tempo deployed to dev. Platform Overview dashboard loaded. | 8 | DevOps | Grafana shows live metrics from kube-system pods. |
| NATS JetStream (dev): 3-node cluster running. Test producer and consumer verified. Core streams created. | 5 | Backend | nats sub quiz.submitted receives test message from nats pub. |
| Database schema: Flyway V001–V003 (all 32 tables). pgbouncer sidecar pattern tested. | 8 | Backend | All 32 tables present. INSERT and SELECT from each schema succeed. |
| Local development: docker-compose.yml for full local stack (all services stubs). README with setup in <15 min. | 5 | Engineering Lead | New engineer runs docker-compose up and hits local API within 15 min. |
| Definition of Done + Definition of Ready: agreed by full team. Written in team_agreements.md. | 3 | Product Owner | PO, QA Lead, Engineering Lead all sign off on written DoD and DoR. |
| Sprint 0 total | 89 SP | All | Dev environment fully functional. |

# 6. Sprint 1 — Core Platform: Auth, Onboarding, Quiz Engine (Weeks 3–4)

| Sprint stats | Value |
| --- | --- |
| Sprint 1 SP target | 175 SP SP |
| P0 stories | 168 SP SP |
| P1 stories | 7 SP SP |
| P2 stories | 0 SP SP |
| Team focus | Authentication, guest screening, exam selection, practice quiz session, basic quiz results. This sprint delivers the core loop: arrive → register → take quiz → see results. |

## Sprint goals

By end of Sprint 1: A new user can discover the platform, take a free screening test, register, select their exam, take a practice quiz, and see their results.

All P0 authentication stories are done. The quiz session works end-to-end for PRACTICE mode. Basic profile is functional.

The adaptive engine skeleton exists and can be called — even if it returns stub data. This unblocks Sprint 2 full integration.

## Stories

| Rank | Story ID | Epic | Actor | User want (abbreviated) | SP | Pri | MoSCoW | Depends on |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | STU-REQ-00A | EPIC-01 | Guest | Take screening test without registering | 5 | P0 | Must | None |
| 2 | STU-REQ-00B | EPIC-01 | Guest | Select exam before screening questions served | 3 | P0 | Must | STU-REQ-00A |
| 3 | STU-REQ-00C | EPIC-01 | Guest | See 10–20 curated exam questions from admin bank | 3 | P0 | Must | STU-REQ-00B |
| 4 | STU-REQ-00D | EPIC-01 | Guest | See full results immediately after submission | 5 | P0 | Must | STU-REQ-00C |
| 5 | STU-REQ-00E | EPIC-01 | System | Auto-save screening results on registration | 3 | P0 | Must | STU-REQ-00D, STU-REQ-01 |
| 6 | STU-REQ-00F | EPIC-01 | System | Set 90-day cookie + fingerprint on test complete | 2 | P0 | Must | STU-REQ-00D |
| 7 | STU-REQ-00G | EPIC-01 | Guest | Show sign-up wall to returning unregistered guest | 2 | P0 | Must | STU-REQ-00F |
| 8 | STU-REQ-00H | EPIC-01 | System | Redirect authenticated user from /screening to /dashboard | 1 | P1 | Should | STU-REQ-01 |
| 9 | STU-REQ-01 | EPIC-02 | Student | Register with email + password | 5 | P0 | Must | None |
| 10 | STU-REQ-02 | EPIC-02 | Student | Sign in with Google (OAuth 2.0 OIDC) | 5 | P0 | Must | None |
| 11 | STU-REQ-03 | EPIC-02 | Student | Login via OTP (email or phone) | 5 | P0 | Must | STU-REQ-01 |
| 12 | STU-REQ-04 | EPIC-02 | Student | Reset password via email link | 3 | P0 | Must | STU-REQ-01 |
| 13 | STU-REQ-05 | EPIC-02 | Student | Accept ToS at registration — stored with version + timestamp | 3 | P0 | Must | STU-REQ-01 |
| 14 | STU-REQ-06 | EPIC-02 | Student | Join via institution invite link | 5 | P0 | Must | STU-REQ-01 |
| 15 | STU-REQ-07 | EPIC-02 | System | Invite link expires after 7 days | 2 | P0 | Must | STU-REQ-06 |
| 16 | STU-REQ-08 | EPIC-02 | Student | Session persists 30 days. Auto-logout after inactivity | 3 | P0 | Must | STU-REQ-01 |
| 17 | STU-REQ-09 | EPIC-02 | Student | Logout from current or all devices | 2 | P0 | Must | STU-REQ-08 |
| 18 | STU-REQ-10 | EPIC-02 | System | Account lockout after 5 failed logins (15 min) | 3 | P0 | Must | STU-REQ-01 |
| 19 | STU-REQ-11 | EPIC-02 | Student | Delete own account (soft delete, hard delete in 30 days) | 3 | P0 | Must | STU-REQ-01 |
| 20 | STU-REQ-12 | EPIC-03 | System | Block all routes until at least one exam selected | 5 | P0 | Must | STU-REQ-01 |
| 21 | STU-REQ-13 | EPIC-03 | Student | Add or change exams at any time | 3 | P0 | Must | STU-REQ-12 |
| 22 | STU-REQ-18 | EPIC-03 | Student | Edit any profile detail at any time | 3 | P0 | Must | STU-REQ-01 |
| 23 | STU-REQ-31 | EPIC-05 | Student | Start a PRACTICE quiz (topic picker, question count shown) | 5 | P0 | Must | STU-REQ-12 |
| 24 | STU-REQ-34 | EPIC-05 | Student | Answer MCQ_SINGLE, MCQ_MULTI, NUMERIC questions | 5 | P0 | Must | STU-REQ-31 |
| 25 | STU-REQ-35 | EPIC-05 | System | Timer shown — soft for practice, hard for mock (auto-submit) | 5 | P0 | Must | STU-REQ-31 |
| 26 | STU-REQ-36 | EPIC-05 | Student | Pause and resume practice quiz (7-day Redis TTL) | 5 | P0 | Must | STU-REQ-31 |
| 27 | STU-REQ-37 | EPIC-05 | Student | See full results immediately on submit (<500ms p95) | 5 | P0 | Must | STU-REQ-34 |
| 28 | STU-REQ-39 | EPIC-05 | Student | Submit a doubt on any question from results screen | 3 | P0 | Must | STU-REQ-37 |
| 29 | ADM-REQ-15 | EPIC-10 | Admin | Configure exam syllabuses and topic weightages | 5 | P0 | Must | Sprint 0 schema |
| 30 | ADM-REQ-16 | EPIC-10 | Admin | Configure screening test question sets per exam | 3 | P0 | Must | ADM-REQ-15 |
| 31 | EXP-REQ-10 | EPIC-08 | Expert | Create and upload a single question (saved as DRAFT) | 5 | P0 | Must | STU-REQ-01 |
| 32 | EXP-REQ-11 | EPIC-08 | Expert | Bulk upload CSV/JSON (≤500 sync, >500 async) | 8 | P0 | Must | EXP-REQ-10 |
| 33 | EXP-REQ-12 | EPIC-08 | Expert | Submit question for peer review queue | 3 | P0 | Must | EXP-REQ-10 |
| 34 | MOD-REQ-03 | EPIC-09 | Moderator | Review question content in moderation queue | 3 | P0 | Must | EXP-REQ-12 |
| 35 | MOD-REQ-04 | EPIC-09 | Moderator | Approve question — enters quiz bank immediately | 3 | P0 | Must | MOD-REQ-03 |
| 36 | STU-REQ-14 | EPIC-03 | Student | Set language preference (EN/HI) during onboarding | 3 | P1 | Should | STU-REQ-12 |

# 7. Sprint 2 — Learning Engine, Analytics, Payments (Weeks 5–6)

| Sprint stats | Value |
| --- | --- |
| Sprint 2 SP target | 187 SP SP |
| P0 stories | 175 SP SP |
| P1 stories | 12 SP SP |
| P2 stories | 0 SP SP |
| Team focus | Adaptive quiz engine, mock tests, analytics dashboard, readiness score, premium subscription, course catalogue, content discovery. Sprint 2 completes the MVP. |

## Sprint goals

By end of Sprint 2: The platform is monetisable. Adaptive quiz, readiness score, and premium subscription all work. A paying user has a complete, differentiated experience.

All MVP P0 stories are done after Sprint 2. The go/no-go checklist becomes applicable at the end of this sprint.

Creator workflow and moderation pipeline must be fully functional — question bank must have ≥200 questions per major exam.

## Stories

| Rank | Story ID | Epic | Actor | User want (abbreviated) | SP | Pri | MoSCoW | Depends on |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 37 | STU-REQ-32 | EPIC-05 | Student | Start ADAPTIVE quiz (platform selects topic + difficulty) | 8 | P0 | Must | STU-REQ-12, Adaptive Engine |
| 38 | STU-REQ-33 | EPIC-05 | Student | Start MOCK test (simulates full exam format, hard timer) | 8 | P0 | Must | STU-REQ-35 |
| 39 | STU-REQ-38 | EPIC-05 | Student | Retry incorrect questions (stored as separate attempt) | 3 | P1 | Should | STU-REQ-37 |
| 40 | STU-REQ-40 | EPIC-05 | Student | See personalised next-action recommendation after quiz (premium) | 5 | P0 | Must | STU-REQ-37, Analytics |
| 41 | STU-REQ-21 | EPIC-04 | Student | Home feed: personalised Continue + Recommended cards | 5 | P0 | Must | STU-REQ-12 |
| 42 | STU-REQ-22 | EPIC-04 | Student | Continue where I left off — last accessed course per exam | 3 | P0 | Must | STU-REQ-24 |
| 43 | STU-REQ-23 | EPIC-04 | Student | Pinned assigned content for institution students | 3 | P0 | Must | STU-REQ-06 |
| 44 | STU-REQ-24 | EPIC-04 | Student | Browse full catalogue: Exam → Subject → Topic hierarchy | 5 | P0 | Must | ADM-REQ-15 |
| 45 | STU-REQ-25 | EPIC-04 | Student | Filter catalogue by exam, subject, topic, difficulty | 3 | P0 | Must | STU-REQ-24 |
| 46 | STU-REQ-26 | EPIC-04 | Student | Full-text search in EN + HI (<500ms p95) | 5 | P0 | Must | OpenSearch setup |
| 47 | STU-REQ-27 | EPIC-04 | Student | View course detail: topics, question count, time, progress | 3 | P0 | Must | STU-REQ-24 |
| 48 | STU-REQ-30 | EPIC-04 | Student | Free students see all content, premium shown with lock | 3 | P0 | Must | Payment stories |
| 49 | STU-REQ-45 | EPIC-06 | Student | See readiness score (0–100) for each exam (premium) | 8 | P0 | Must | Analytics engine, STU-REQ-37 |
| 50 | STU-REQ-46 | EPIC-06 | Student | View score history chart (7D/30D/90D) | 5 | P0 | Must | STU-REQ-45 |
| 51 | STU-REQ-48 | EPIC-06 | Student | See activity summary: quizzes, accuracy, study time, streak | 3 | P0 | Must | STU-REQ-37 |
| 52 | STU-REQ-50 | EPIC-06 | Student | Track study streak and see milestones (7, 30, 100 days) | 3 | P0 | Must | STU-REQ-48 |
| 53 | Payment-01 | EPIC-10 | Student | Create payment intent (Stripe checkout flow) | 8 | P0 | Must | Stripe integration |
| 54 | Payment-02 | EPIC-10 | System | Handle Stripe webhook: payment.succeeded → activate premium | 5 | P0 | Must | Payment-01 |
| 55 | Payment-03 | EPIC-10 | Student | View current subscription status and period | 3 | P0 | Must | Payment-02 |
| 56 | Payment-04 | EPIC-10 | Student | See upgrade prompt and unlock premium features | 3 | P0 | Must | Payment-02 |
| 57 | EXP-REQ-01 | EPIC-08 | Expert | Apply to become a creator (form + sample question) | 3 | P0 | Must | ADM-REQ-17 |
| 58 | EXP-REQ-05 | EPIC-08 | Expert | Submit peer review (cannot review own submissions) | 5 | P0 | Must | EXP-REQ-12 |
| 59 | EXP-REQ-06 | EPIC-08 | Expert | Create course with title, exam, topics (saved as DRAFT) | 5 | P0 | Must | ADM-REQ-15 |
| 60 | EXP-REQ-07 | EPIC-08 | Expert | Preview course exactly as student sees it | 3 | P0 | Must | EXP-REQ-06 |
| 61 | EXP-REQ-08 | EPIC-08 | Expert | Submit course for moderation review (locked during review) | 3 | P0 | Must | EXP-REQ-07 |
| 62 | MOD-REQ-05 | EPIC-09 | Moderator | Return question with min 20-char feedback | 3 | P0 | Must | MOD-REQ-03 |
| 63 | MOD-REQ-06 | EPIC-09 | Moderator | Reject question with predefined reason code | 3 | P0 | Must | MOD-REQ-03 |
| 64 | MOD-REQ-07 | EPIC-09 | Moderator | Approve/return/reject a course (preview as student) | 5 | P0 | Must | MOD-REQ-03 |
| 65 | ADM-REQ-17 | EPIC-10 | Admin | Manage subscription plans and pricing configuration | 5 | P0 | Must | Payment-01 |
| 66 | ADM-REQ-07 | EPIC-10 | Admin | Approve or reject creator application | 3 | P0 | Must | EXP-REQ-01 |
| 67 | ADM-REQ-19 | EPIC-10 | System | Immutable append-only audit log (INSERT only, write-before-execute) | 8 | P0 | Must | Sprint 0 schema |
| 68 | STU-REQ-15 | EPIC-03 | Student | Set target exam date (powers countdown + prediction) | 3 | P1 | Should | STU-REQ-12 |
| 69 | STU-REQ-16 | EPIC-03 | Student | Set daily study goal (calibrates recommendation volume) | 2 | P1 | Should | STU-REQ-12 |
| 70 | STU-REQ-28 | EPIC-04 | Student | Bookmark any course or topic (unlimited) | 3 | P1 | Should | STU-REQ-24 |

# 8. Sprint 3 — Community, Creator, Moderation (Weeks 7–8)

| Sprint stats | Value |
| --- | --- |
| Sprint 3 SP target | 175 SP SP |
| P0 stories | 96 SP SP |
| P1 stories | 69 SP SP |
| P2 stories | 10 SP SP |
| Team focus | Community features, full creator and teacher workflows, complete moderation system, institution management, advanced analytics. Platform becomes collaborative. |

## Sprint goals

By end of Sprint 3: The full content creation pipeline is operational. Community threads, doubts, and leaderboards work. Institutions can enrol students and create assignments.

The moderation system must be fully delivered in Sprint 3 — it is a complete, interconnected workflow that cannot be split across sprints.

Expert creators have all tools they need: dashboard, peer review queue, doubt queue, institution management.

## Stories

| Rank | Story ID | Epic | Actor | User want (abbreviated) | SP | Pri | MoSCoW | Depends on |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 71 | STU-REQ-41 | EPIC-05 | Student | Post discussion thread tagged to exam/subject/topic | 3 | P1 | Should | MOD-REQ-08 |
| 72 | STU-REQ-42 | EPIC-05 | Student | Read and upvote community answers | 2 | P1 | Should | STU-REQ-41 |
| 73 | STU-REQ-43 | EPIC-05 | Student | View global and institution leaderboard | 3 | P1 | Should | STU-REQ-48 |
| 74 | STU-REQ-44 | EPIC-05 | Student | Report inappropriate content (enters moderation queue) | 2 | P1 | Should | MOD-REQ-08 |
| 75 | STU-REQ-51 | EPIC-06 | Student | View topic strength map STRONG/DEVELOPING/WEAK (premium) | 8 | P0 | Must | STU-REQ-45 |
| 76 | STU-REQ-52 | EPIC-06 | Student | Drill into topic detail: accuracy, attempts, avg time | 5 | P0 | Must | STU-REQ-51 |
| 77 | STU-REQ-53 | EPIC-06 | Student | One-tap from topic drill-down to start quiz on that topic | 2 | P1 | Should | STU-REQ-52 |
| 78 | STU-REQ-47 | EPIC-06 | Student | View predicted readiness by target exam date (premium) | 8 | P0 | Must | STU-REQ-45, STU-REQ-15 |
| 79 | STU-REQ-49 | EPIC-06 | Student | Exam countdown shown if target date set | 2 | P1 | Should | STU-REQ-15 |
| 80 | STU-REQ-55 | EPIC-06 | Student | Institution student analytics auto-visible to admin/teacher | 5 | P0 | Must | EXP-REQ-16 |
| 81 | EXP-REQ-04 | EPIC-08 | Expert | View personal dashboard: content stats, queue counts | 3 | P1 | Should | EXP-REQ-12 |
| 82 | EXP-REQ-09 | EPIC-08 | Expert | Edit live course (creates new draft; original stays live) | 5 | P1 | Should | EXP-REQ-08 |
| 83 | EXP-REQ-13 | EPIC-08 | Expert | Review pending question from shared peer queue | 3 | P0 | Must | EXP-REQ-05 |
| 84 | EXP-REQ-14 | EPIC-08 | Expert | Answer student doubts from doubt queue (Expert badge shown) | 5 | P0 | Must | STU-REQ-39 |
| 85 | EXP-REQ-15 | EPIC-08 | Expert | Post to community threads with Teacher/Expert badge | 2 | P1 | Should | STU-REQ-41 |
| 86 | EXP-REQ-16 | EPIC-08 | Teacher | View institution students: progress, readiness, last login | 5 | P0 | Must | STU-REQ-55 |
| 87 | EXP-REQ-17 | EPIC-08 | Teacher | Assign course/quiz to students with optional deadline | 8 | P0 | Must | EXP-REQ-16 |
| 88 | EXP-REQ-18 | EPIC-08 | Teacher | View batch analytics: readiness distribution, weakest topics | 8 | P0 | Must | EXP-REQ-16 |
| 89 | MOD-REQ-01 | EPIC-09 | Moderator | Land on moderation dashboard showing all queue counts | 3 | P0 | Must | Sprint 0 auth |
| 90 | MOD-REQ-02 | EPIC-09 | Moderator | View three queues: content, discussion, behaviour | 3 | P0 | Must | MOD-REQ-01 |
| 91 | MOD-REQ-08 | EPIC-09 | Moderator | Review flagged discussion: APPROVE, REMOVE, ESCALATE | 5 | P0 | Must | STU-REQ-41 |
| 92 | MOD-REQ-09 | EPIC-09 | Moderator | Remove live post (archived not deleted, author notified) | 3 | P0 | Must | MOD-REQ-08 |
| 93 | MOD-REQ-10 | EPIC-09 | Moderator | Issue user warning (3 in 30 days triggers auto-escalation) | 5 | P0 | Must | MOD-REQ-08 |
| 94 | MOD-REQ-11 | EPIC-09 | Moderator | Review behaviour reports: context + warning history | 3 | P0 | Must | MOD-REQ-10 |
| 95 | MOD-REQ-12 | EPIC-09 | Moderator | Escalate to platform admin (cannot suspend/ban) | 3 | P0 | Must | MOD-REQ-11 |
| 96 | ADM-REQ-09 | EPIC-10 | Admin | Create institution with plan, seat count, billing contact | 5 | P0 | Must | Payment-02 |
| 97 | ADM-REQ-10 | EPIC-10 | Admin | View institution performance: students, readiness, billing | 5 | P0 | Must | ADM-REQ-09 |
| 98 | ADM-REQ-04 | EPIC-10 | Admin | Suspend (with duration) or ban user. Reason mandatory. | 5 | P0 | Must | ADM-REQ-19 |
| 99 | ADM-REQ-08 | EPIC-10 | Admin | Grant and revoke admin access. All changes logged. | 3 | P0 | Must | ADM-REQ-19 |
| 100 | ADM-REQ-14 | EPIC-10 | Admin | Process full or partial refund. Reason mandatory. | 5 | P0 | Must | Payment-02, ADM-REQ-19 |
| 101 | STU-REQ-19 | EPIC-03 | Student | Profile completion indicator X/5 with benefit per field | 3 | P1 | Should | STU-REQ-18 |
| 102 | STU-REQ-20 | EPIC-03 | Student | Manage notification preferences by channel and category | 3 | P1 | Should | STU-REQ-01 |
| 103 | STU-REQ-29 | EPIC-04 | Student | View and manage bookmarks grouped by exam with progress | 2 | P1 | Should | STU-REQ-28 |
| 104 | STU-REQ-54 | EPIC-06 | Student | Generate shareable signed read-only progress URL (premium) | 5 | P1 | Should | STU-REQ-45 |
| 105 | EXP-REQ-02 | EPIC-08 | Expert | Join via direct invite link (7-day expiry, instant access) | 3 | P1 | Should | STU-REQ-06 |
| 106 | EXP-REQ-03 | EPIC-08 | Expert | Join via institution (scoped access, added by institution admin) | 3 | P1 | Should | ADM-REQ-09 |
| 107 | ADM-REQ-18 | EPIC-10 | Admin | Manage moderation team: grant access, view activity | 3 | P1 | Should | MOD-REQ-01 |
| 108 | STU-REQ-17 | EPIC-03 | Student | Upload profile photo (JPG/PNG/WEBP, max 5MB) | 2 | P2 | Could | STU-REQ-01 |
| 109 | STU-REQ-43 | EPIC-05 | Student | Leaderboard: global by exam + institution leaderboard | 3 | P2 | Could | STU-REQ-48 |
| 110 | ADM-REQ-05 | EPIC-10 | Admin | Impersonate user in read-only mode (every session logged) | 5 | P1 | Should | ADM-REQ-19 |

# 9. Sprint 4 — Admin, Institution, Polish, Launch Prep (Weeks 9–10)

| Sprint stats | Value |
| --- | --- |
| Sprint 4 SP target | 165 SP SP |
| P0 stories | 0 SP SP |
| P1 stories | 108 SP SP |
| P2 stories | 27 SP SP |
| Team focus | Admin portal completion, post-exam experience, remaining P1 analytics, announcement system, load testing, security pen test support, go-live preparation. |

## Sprint goals

By end of Sprint 4: All P0 and P1 stories are complete. Platform is launch-ready. Load test passed. Security pen test remediated. Store approvals received.

Sprint 4 allocates 30% of engineering time to non-feature work: regression testing, load testing, security pen test support, performance optimisation.

No new features are introduced in the final week. Only bug fixing, performance tuning, and launch preparation.

## Stories

| Rank | Story ID | Epic | Actor | User want (abbreviated) | SP | Pri | MoSCoW | Depends on |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 111 | ADM-REQ-01 | EPIC-10 | Admin | Platform KPI dashboard with all key metrics | 8 | P1 | Should | All analytics stories |
| 112 | ADM-REQ-02 | EPIC-10 | Admin | Drill-down dashboards per module (users, content, finance) | 5 | P1 | Should | ADM-REQ-01 |
| 113 | ADM-REQ-03 | EPIC-10 | Admin | Search and view any user by name/email/role | 3 | P1 | Should | Sprint 0 auth |
| 114 | ADM-REQ-11 | EPIC-10 | Admin | Revenue dashboard: MTD, subscriptions, churn | 5 | P1 | Should | Payment-02 |
| 115 | ADM-REQ-12 | EPIC-10 | Admin | Manage subscriptions: upgrade, downgrade, pause, comp | 5 | P1 | Should | Payment-02 |
| 116 | ADM-REQ-13 | EPIC-10 | Admin | Institution billing: plan, seats, invoices, mark paid | 5 | P1 | Should | ADM-REQ-09 |
| 117 | ADM-REQ-20 | EPIC-10 | Admin | Send platform-wide announcement by channel and segment | 5 | P1 | Should | Notification Service |
| 118 | ADM-REQ-06 | EPIC-10 | Admin | Merge duplicate accounts (history + subscriptions merged) | 5 | P1 | Should | ADM-REQ-03 |
| 119 | STU-REQ-56 | EPIC-07 | Student | Exam day notification at 07:00 local with readiness score | 3 | P1 | Should | STU-REQ-15 |
| 120 | STU-REQ-57 | EPIC-07 | Student | Auto-generate shareable certificate (PNG + link) for premium | 5 | P1 | Should | STU-REQ-33, Payment-02 |
| 121 | STU-REQ-60 | EPIC-07 | Student | 'What's next' prompt within 7 days of exam date | 2 | P1 | Should | STU-REQ-15 |
| 122 | STU-REQ-61 | EPIC-07 | Student | Add new exam at any time — fresh score, history preserved | 3 | P0 | Must | STU-REQ-13 |
| 123 | STU-REQ-62 | EPIC-07 | Student | Skill-based courses catalogue separate from exam prep | 5 | P1 | Should | EXP-REQ-06 |
| 124 | STU-REQ-63 | EPIC-07 | Student | Lifetime learning profile — all history permanent | 3 | P1 | Should | STU-REQ-45 |
| 125 | ADM-REQ-07 | EPIC-10 | Admin | Approve creator applications with sample question review | 3 | P1 | Should | EXP-REQ-01 |
| 126 | EXP-REQ-17b | EPIC-08 | Teacher | Send assignment reminder (rate limited 1/24hr) | 3 | P1 | Should | EXP-REQ-17 |
| 127 | STU-REQ-58 | EPIC-07 | Student | Log actual exam result (stored privately) | 2 | P2 | Could | STU-REQ-15 |
| 128 | STU-REQ-59 | EPIC-07 | Student | Compare predicted vs actual result (premium) | 3 | P2 | Could | STU-REQ-47, STU-REQ-58 |
| 129 | STU-REQ-54b | EPIC-06 | Student | Revoke shareable progress link | 1 | P1 | Should | STU-REQ-54 |
| 130 | TECH-LT-01 | Technical | DevOps | Load test: 500 concurrent users, all critical paths | 8 | P0 | Must | All services done |
| 131 | TECH-PT-01 | Technical | Security | Penetration test: IDOR, SQLi, auth bypass, mobile | 13 | P0 | Must | All services done |
| 132 | TECH-PT-02 | Technical | Security | Penetration test: remediation of all CRITICAL findings | 8 | P0 | Must | TECH-PT-01 |
| 133 | TECH-APP-01 | Technical | Mobile | iOS App Store submission and approval | 5 | P0 | Must | All iOS stories done |
| 134 | TECH-APP-02 | Technical | Mobile | Android Play Store submission and approval | 5 | P0 | Must | All Android stories done |
| 135 | TECH-LGL-01 | Technical | Legal | ToS + Privacy Policy legal review and sign-off | 3 | P0 | Must | Legal team |
| 136 | TECH-LGL-02 | Technical | Legal | Data processing agreements with Stripe, Twilio, SendGrid | 2 | P0 | Must | Legal team |
| 137 | TECH-MON-01 | Technical | DevOps | All Grafana dashboards verified showing live data | 3 | P0 | Must | Monitoring Sprint 0 |
| 138 | TECH-MON-02 | Technical | DevOps | PagerDuty alert routing verified (test alert fired + ack) | 2 | P0 | Must | TECH-MON-01 |

# 11. Dependency Map

Critical dependencies that, if delayed, cause downstream stories to be blocked. Engineering Lead reviews this map at every sprint planning to identify risk.

Critical Path — Must be done in this order

| Dependency chain | Blocker story | Blocked stories | Risk if delayed |
| --- | --- | --- | --- |
| Database schema → Everything | Sprint 0: All 32 tables created | All 113 feature stories | 1-day delay in Sprint 0 = 1-day delay to Sprint 1 start |
| Auth (register/login) → All user features | STU-REQ-01 | STU-REQ-12, 31, all EPIC-03–07, all creator stories | Auth must be complete in Sprint 1 Week 1. No other features start without it. |
| Exam syllabus config → Quiz, catalogue, analytics | ADM-REQ-15 | STU-REQ-24, 31, 32, 45, 51 | Admin must configure exams in Sprint 1. Quiz bank cannot be built without exam structure. |
| Question upload + moderation → Quiz bank | EXP-REQ-10–12 + MOD-REQ-03–06 | STU-REQ-31, 32, 33 (need questions to serve) | Content pipeline must run in parallel with quiz engine. Minimum 50 questions needed for Sprint 2 testing. |
| Payment integration → Premium features | Payment-01, Payment-02 | STU-REQ-40, 45, 47, 51, 57, STU-REQ-30 | Stripe integration in Sprint 2. All premium-gated features blocked until payment webhook works. |
| Analytics engine → Readiness score | STU-REQ-45 (score computation) | STU-REQ-46, 47, 51, 52, STU-REQ-40 (recommendation) | Analytics service must have working score algorithm before Sprint 2 ends. |
| Adaptive engine → Adaptive quiz | Adaptive Engine (STU-REQ-32 depends on gRPC call) | STU-REQ-32, STU-REQ-40 | Adaptive Engine must have working topic selection before Sprint 2 Week 1. |
| Institution creation → Teacher workflow | ADM-REQ-09 | EXP-REQ-16, 17, 18, STU-REQ-55 | Cannot test teacher features without at least one institution in the system. |

External Dependencies

| External dependency | Owned by | When needed | Risk mitigation |
| --- | --- | --- | --- |
| Stripe account + test API keys | Product Owner / Finance | Sprint 2 Week 1 | Create Stripe account in Sprint 0. Test keys available from day 1. |
| Apple Developer Program membership | Product Owner | Sprint 1 | Must already be active. App ID provisioned in Sprint 1. |
| Google Play Console account | Product Owner | Sprint 1 | Must already be active. App signing configured in Sprint 1. |
| Twilio account (OTP SMS) | DevOps / Finance | Sprint 1 (OTP login) | Create and fund in Sprint 0. Test mode available immediately. |
| SendGrid account (email) | DevOps | Sprint 1 (email verification) | Create and verify sender domain in Sprint 0. |
| Firebase FCM setup | Mobile Engineer | Sprint 2 (push notifications) | Firebase project created in Sprint 1. Not blocking until Sprint 2. |
| Third-party pen test firm | Engineering Lead / Security | Sprint 4 (4 weeks lead time) | Engage firm at end of Sprint 2. Schedule for Sprint 4 Week 2. |
| Legal firm for ToS/Privacy Policy review | Product Owner / Legal | Sprint 4 | Engage at start of Sprint 3. 4-week review timeline. |

# 12. Backlog Health Metrics & Definition of Ready

## 12.1 Definition of Ready (DoR)

A story must satisfy ALL of the following before it can be pulled into a sprint. Stories that do not meet DoR are returned to the Product Owner for refinement.

| Criterion | How to verify |
| --- | --- |
| User story is written in standard format: As a [actor], I want [capability], so that [business value] | Story text in Jira/ADO matches this format exactly |
| Acceptance criteria are written in Gherkin (Given/When/Then) — minimum 3 scenarios | Story has ≥3 Gherkin scenarios attached in the acceptance criteria field |
| Story is estimated in story points by the engineering team | Story has a numeric SP value agreed in planning poker (not just PO estimate) |
| Dependencies are identified and dependency stories are in DONE or IN_PROGRESS | Dependency field in Jira is filled. Blocking stories are verified as unblocked. |
| Design (UI/UX) is available for all user-facing screens in the story | Figma link attached to story. Designer has marked screen as 'Ready for Dev' |
| API contract is defined (endpoint, request/response schema) for backend stories | OpenAPI spec section or API contract doc linked from story |
| Database schema changes are identified and Flyway migration is written/planned | Schema change noted in story. Migration file created in PR or planned. |
| Security considerations documented (does this story touch auth, PII, payments?) | Security notes field in story template filled. Security Lead consulted if needed. |
| Story fits in one sprint (≤ 13 SP). Anything larger is split. | SP ≤ 13. If 21, it must be split before entering sprint. |
| Product Owner has accepted the story (clicked 'Ready' in Jira/ADO) | PO status field = READY |

## 12.2 Definition of Done (DoD)

A story is DONE when ALL of the following are true. Engineers self-certify before moving to Done. QA Lead verifies independently.

| Criterion | Verified by |
| --- | --- |
| All Gherkin acceptance criteria pass — automated or manual test evidence attached | QA Lead |
| Unit tests written for all business logic (coverage does not decrease below 80%) | Engineering Lead (code review) |
| Integration tests pass for all API endpoints touched by this story | QA Lead + CI pipeline |
| Code reviewed by at least 1 other engineer (not the author). PR approved. | PR approval in GitHub |
| No open Priority 1 or Priority 2 bugs raised against this story | QA Lead — Jira bug count = 0 (P1+P2) |
| Security checklist completed: IDOR test, input validation, auth check (if applicable) | Engineer + code review |
| Logging: all security events audited. No PII in logs. | Code review |
| API documentation updated in OpenAPI spec (if endpoint added or changed) | Engineering Lead |
| Database migration tested on staging: forward migration runs clean | DevOps / Backend engineer |
| Performance: endpoint meets p95 target from NFR spec (checked in staging load test) | QA Lead (load test results) |
| Deployed to staging and smoke-tested by QA Lead | QA Lead |
| Product Owner has accepted the story in staging (clicked 'Accept' in Jira/ADO) | Product Owner |

## 12.3 Backlog Health Indicators

| Metric | Target | Action if breached |
| --- | --- | --- |
| P0 stories in Sprint 1–2 | 100% of P0 SP in Sprint 1–2 slots | Re-prioritise immediately. Escalate to PO and Engineering Lead. |
| Stories meeting DoR at Sprint Planning | ≥ 90% of next sprint stories meet DoR | Refinement session before planning. PO + BA to unblock stories. |
| Backlog refinement frequency | Weekly, every Thursday 1 hour | If skipped > 1 week, next sprint planning will be under-prepared. |
| Open bugs (P1+P2) at sprint end | ≤ 5 P2 bugs, 0 P1 bugs | Zero P1: hard requirement. Carry-over P2 bugs count against next sprint velocity. |
| Velocity variance | ± 20% from target | < 160 SP: cut P2 stories. < 140 SP: escalate to PO for scope decision. |
| Stories not estimated | 0 unestimated stories in current sprint | Block from sprint. Return to refinement. |
| Won't stories in active sprints | 0 Won't stories ever assigned to a sprint | Won't = Phase 2 parking lot. No exceptions. |